## Project_Summary
Project_ID | Project_Name | Start_Date | Planned_End_Date | Progress_% | Planned_% | Budget_USD | Actual_Spend_USD | Schedule_Delay_Days | Critical_Blockers | Open_Risks | Stakeholder_Sentiment | Resource_Utilization_% | RAG_Status
S2P-001 | ERP Migration | 2026-01-10 | 2026-08-30 | 60 | 75 | 500000 | 420000 | 12 | 1 | 5 | Neutral | 88 | Amber
S2P-002 | CRM Upgrade | 2026-02-15 | 2026-09-20 | 42 | 68 | 450000 | 430000 | 18 | 2 | 8 | Negative | 97 | Red
S2P-003 | AI Procurement | 2026-03-01 | 2026-10-15 | 90 | 92 | 800000 | 700000 | 2 | 0 | 1 | Positive | 72 | Green
S2P-006 | Supplier Portal Upgrade | 2026-05-01 | 2026-12-20 | 74 | 80 | 720000 | 610000 | 6 | 1 | 3 | Neutral | 82 | Amber
S2P-007 | Data Lake Modernization | 2026-02-10 | 2026-11-30 | 88 | 86 | 1500000 | 1210000 | 1 | 0 | 2 | Positive | 77 | Green
S2P-008 | Vendor Risk Platform | 2026-03-15 | 2026-10-15 | 39 | 62 | 580000 | 560000 | 21 | 3 | 8 | Negative | 97 | Red
S2P-009 | Invoice Automation | 2026-04-12 | 2026-09-28 | 79 | 81 | 430000 | 350000 | 4 | 0 | 2 | Positive | 73 | Green
S2P-010 | Contract Lifecycle Mgmt | 2026-01-18 | 2026-10-31 | 58 | 72 | 980000 | 905000 | 14 | 2 | 6 | Neutral | 91 | Amber

## Budget_Tracking
Project_ID | Month | Planned | Actual | Variance
S2P-001 | Jan | 50000 | 52000 | 2000
S2P-001 | Feb | 60000 | 65000 | 5000
S2P-001 | Mar | 70000 | 68000 | -2000
S2P-002 | Jan | 50000 | 52000 | 2000
S2P-002 | Feb | 60000 | 65000 | 5000
S2P-002 | Mar | 70000 | 68000 | -2000
S2P-003 | Jan | 50000 | 52000 | 2000
S2P-003 | Feb | 60000 | 65000 | 5000
S2P-003 | Mar | 70000 | 68000 | -2000
S2P-006 | Jan | 85275 | 81602 | -3673
S2P-006 | Feb | 108184 | 112238 | 4054
S2P-006 | Mar | 91108 | 99730 | 8622
S2P-006 | Apr | 114650 | 112063 | -2587
S2P-007 | Jan | 72252 | 75835 | 3583
S2P-007 | Feb | 105613 | 101420 | -4193
S2P-007 | Mar | 95038 | 109470 | 14432
S2P-007 | Apr | 70028 | 85111 | 15083
S2P-008 | Jan | 70485 | 86053 | 15568
S2P-008 | Feb | 86128 | 96134 | 10006
S2P-008 | Mar | 115088 | 110356 | -4732
S2P-008 | Apr | 82281 | 78596 | -3685
S2P-009 | Jan | 88174 | 95029 | 6855
S2P-009 | Feb | 87254 | 89815 | 2561
S2P-009 | Mar | 108285 | 105141 | -3144
S2P-009 | Apr | 115068 | 115518 | 450
S2P-010 | Jan | 105647 | 112426 | 6779
S2P-010 | Feb | 116194 | 127212 | 11018
S2P-010 | Mar | 71893 | 69917 | -1976
S2P-010 | Apr | 51523 | 69356 | 17833

## Milestones
Project_ID | Milestone | Status | Planned_Date | Actual_Date
S2P-001 | Requirements | Completed | 2026-07-01 | 2026-07-05
S2P-001 | Design | Completed | 2026-07-01 | 2026-07-05
S2P-001 | Development | Delayed | 2026-07-01 | 2026-07-05
S2P-001 | Testing | In Progress | 2026-07-01 | 2026-07-05
S2P-001 | Go Live | Pending | 2026-07-01 | 2026-07-05
S2P-002 | Requirements | Completed | 2026-07-01 | 2026-07-05
S2P-002 | Design | Completed | 2026-07-01 | 2026-07-05
S2P-002 | Development | Delayed | 2026-07-01 | 2026-07-05
S2P-002 | Testing | In Progress | 2026-07-01 | 2026-07-05
S2P-002 | Go Live | Pending | 2026-07-01 | 2026-07-05
S2P-003 | Requirements | Completed | 2026-07-01 | 2026-07-05
S2P-003 | Design | Completed | 2026-07-01 | 2026-07-05
S2P-003 | Development | Delayed | 2026-07-01 | 2026-07-05
S2P-003 | Testing | In Progress | 2026-07-01 | 2026-07-05
S2P-003 | Go Live | Pending | 2026-07-01 | 2026-07-05
S2P-006 | Requirements | Completed | 2026-07-01 | 2026-07-05
S2P-006 | Design | Completed | 2026-07-01 | 2026-07-05
S2P-006 | Development | Delayed | 2026-07-01 | 2026-07-05
S2P-006 | Testing | In Progress | 2026-07-01 | 2026-07-05
S2P-006 | Go Live | Completed | 2026-07-01 | 2026-07-05
S2P-007 | Requirements | Delayed | 2026-07-01 | 2026-07-05
S2P-007 | Design | Delayed | 2026-07-01 | 2026-07-05
S2P-007 | Development | In Progress | 2026-07-01 | 2026-07-05
S2P-007 | Testing | Completed | 2026-07-01 | 2026-07-05
S2P-007 | Go Live | In Progress | 2026-07-01 | 2026-07-05
S2P-008 | Requirements | Completed | 2026-07-01 | 2026-07-05
S2P-008 | Design | Completed | 2026-07-01 | 2026-07-05
S2P-008 | Development | In Progress | 2026-07-01 | 2026-07-05
S2P-008 | Testing | Completed | 2026-07-01 | 2026-07-05
S2P-008 | Go Live | In Progress | 2026-07-01 | 2026-07-05
S2P-009 | Requirements | Completed | 2026-07-01 | 2026-07-05
S2P-009 | Design | Completed | 2026-07-01 | 2026-07-05
S2P-009 | Development | In Progress | 2026-07-01 | 2026-07-05
S2P-009 | Testing | Delayed | 2026-07-01 | 2026-07-05
S2P-009 | Go Live | Completed | 2026-07-01 | 2026-07-05
S2P-010 | Requirements | In Progress | 2026-07-01 | 2026-07-05
S2P-010 | Design | Completed | 2026-07-01 | 2026-07-05
S2P-010 | Development | In Progress | 2026-07-01 | 2026-07-05
S2P-010 | Testing | Completed | 2026-07-01 | 2026-07-05
S2P-010 | Go Live | Delayed | 2026-07-01 | 2026-07-05

## Risk_Register
Risk_ID | Project_ID | Risk | Severity | Status
R001 | S2P-001 | Risk 1 | Critical | Open
R002 | S2P-002 | Risk 2 | Medium | Open
R003 | S2P-002 | Risk 3 | High | Open
R004 | S2P-001 | Risk 4 | Medium | Open
R005 | S2P-002 | Risk 5 | Critical | Open
R006 | S2P-001 | Risk 6 | High | Open
R007 | S2P-002 | Risk 7 | Critical | Open
R008 | S2P-001 | Risk 8 | High | Open
R009 | S2P-003 | Risk 9 | High | Open
RNEW148 | S2P-006 | Scope Creep | Medium | Open
RNEW132 | S2P-006 | Scope Creep | Medium | Open
RNEW149 | S2P-006 | Security | Medium | Open
RNEW222 | S2P-007 | Security | Critical | Open
RNEW296 | S2P-007 | Vendor Delay | Medium | Open
RNEW237 | S2P-007 | Scope Creep | Critical | Open
RNEW373 | S2P-008 | Vendor Delay | Medium | Open
RNEW348 | S2P-008 | Vendor Delay | High | Open
RNEW366 | S2P-008 | Vendor Delay | High | Open
RNEW474 | S2P-009 | Scope Creep | Critical | Open
RNEW439 | S2P-009 | Vendor Delay | High | Open
RNEW487 | S2P-009 | Vendor Delay | High | Open
RNEW559 | S2P-010 | Security | Critical | Open
RNEW591 | S2P-010 | Vendor Delay | Critical | Open
RNEW580 | S2P-010 | Vendor Delay | Critical | Open

## Issue_Log
Issue_ID | Project_ID | Issue | Priority | Status
I001 | S2P-003 | Issue 1 | P1 | Resolved
I002 | S2P-003 | Issue 2 | P2 | Open
I003 | S2P-002 | Issue 3 | P3 | Resolved
I004 | S2P-001 | Issue 4 | P2 | Open
I005 | S2P-003 | Issue 5 | P3 | Open
I006 | S2P-001 | Issue 6 | P1 | Resolved
I007 | S2P-001 | Issue 7 | P2 | Open
I008 | S2P-002 | Issue 8 | P3 | Open
I009 | S2P-002 | Issue 9 | P1 | Open
INEW1 | S2P-006 | Integration issue | P2 | Open
INEW2 | S2P-007 | Integration issue | P2 | Open
INEW3 | S2P-008 | Integration issue | P2 | Open
INEW4 | S2P-009 | Integration issue | P1 | Open
INEW5 | S2P-010 | Integration issue | P1 | Open

## Resource_Allocation
Project_ID | Role | Utilization_%
S2P-001 | Developer | 90
S2P-001 | QA | 85
S2P-001 | PM | 75
S2P-002 | Developer | 90
S2P-002 | QA | 85
S2P-002 | PM | 75
S2P-003 | Developer | 90
S2P-003 | QA | 85
S2P-003 | PM | 75
S2P-006 | Developer | 88
S2P-006 | QA | 78
S2P-006 | PM | 96
S2P-007 | Developer | 87
S2P-007 | QA | 82
S2P-007 | PM | 76
S2P-008 | Developer | 71
S2P-008 | QA | 88
S2P-008 | PM | 85
S2P-009 | Developer | 81
S2P-009 | QA | 93
S2P-009 | PM | 94
S2P-010 | Developer | 92
S2P-010 | QA | 71
S2P-010 | PM | 84

## Stakeholder_Feedback
Project_ID | Week | Sentiment | Comment
S2P-001 | W1 | Neutral | Weekly review
S2P-001 | W1 | Neutral | Weekly review
S2P-002 | W1 | Negative | Weekly review
S2P-002 | W1 | Negative | Weekly review
S2P-003 | W1 | Positive | Weekly review
S2P-003 | W1 | Positive | Weekly review
S2P-006 | W1 | Positive | Auto generated feedback
S2P-007 | W1 | Positive | Auto generated feedback
S2P-008 | W1 | Negative | Auto generated feedback
S2P-009 | W1 | Positive | Auto generated feedback
S2P-010 | W1 | Neutral | Auto generated feedback

## Weekly_Status
Project_ID | Week | Progress_% | Spend | Blockers | RAG
S2P-001 | W1 | 60 | 100000 | 1 | Amber
S2P-001 | W2 | 60 | 100000 | 1 | Amber
S2P-001 | W3 | 60 | 100000 | 1 | Amber
S2P-002 | W1 | 42 | 100000 | 1 | Amber
S2P-002 | W2 | 42 | 100000 | 1 | Amber
S2P-002 | W3 | 42 | 100000 | 1 | Amber
S2P-003 | W1 | 90 | 100000 | 1 | Amber
S2P-003 | W2 | 90 | 100000 | 1 | Amber
S2P-003 | W3 | 90 | 100000 | 1 | Amber
S2P-006 | W1 | 56 | 130226 | 2 | Red
S2P-006 | W2 | 67 | 122530 | 0 | Amber
S2P-006 | W3 | 37 | 87031 | 0 | Amber
S2P-006 | W4 | 92 | 93727 | 2 | Amber
S2P-007 | W1 | 65 | 109911 | 2 | Amber
S2P-007 | W2 | 58 | 179812 | 0 | Red
S2P-007 | W3 | 63 | 172025 | 0 | Red
S2P-007 | W4 | 87 | 135701 | 1 | Red
S2P-008 | W1 | 75 | 153517 | 1 | Amber
S2P-008 | W2 | 71 | 128731 | 2 | Green
S2P-008 | W3 | 95 | 170112 | 1 | Red
S2P-008 | W4 | 89 | 148796 | 2 | Red
S2P-009 | W1 | 71 | 165477 | 2 | Red
S2P-009 | W2 | 93 | 164020 | 2 | Red
S2P-009 | W3 | 58 | 114703 | 1 | Amber
S2P-009 | W4 | 67 | 149507 | 1 | Amber
S2P-010 | W1 | 68 | 113225 | 2 | Amber
S2P-010 | W2 | 51 | 131118 | 2 | Green
S2P-010 | W3 | 66 | 178729 | 1 | Amber
S2P-010 | W4 | 61 | 137789 | 2 | Red