## Project_Summary
Project_ID | Project_Name | Start_Date | Planned_End_Date | Progress_% | Planned_% | Budget_USD | Actual_Spend_USD | Schedule_Delay_Days | Critical_Blockers | Open_Risks | Stakeholder_Sentiment | Resource_Utilization_% | RAG_Status
S2P-001 | ERP Migration | 2026-01-10 | 2026-08-30 | 60 | 75 | 500000 | 420000 | 12 | 1 | 5 | Neutral | 88 | Amber
S2P-002 | CRM Upgrade | 2026-02-15 | 2026-09-20 | 42 | 68 | 450000 | 430000 | 18 | 2 | 8 | Negative | 97 | Red
S2P-003 | AI Procurement | 2026-03-01 | 2026-10-15 | 90 | 92 | 800000 | 700000 | 2 | 0 | 1 | Positive | 72 | Green

## Budget_Tracking
Project_ID | Month | Planned | Actual | Variance
S2P-001 | Jan | 50000 | 52000 | 2000
S2P-001 | Feb | 60000 | 65000 | 5000
S2P-001 | Mar | 70000 | 68000 | -2000
S2P-002 | Jan | 50000 | 52000 | 2000
S2P-002 | Feb | 60000 | 65000 | 5000
S2P-002 | Mar | 70000 | 68000 | -2000
S2P-003 | Jan | 50000 | 52000 | 2000
S2P-003 | Feb | 60000 | 65000 | 5000
S2P-003 | Mar | 70000 | 68000 | -2000

## Milestones
Project_ID | Milestone | Status | Planned_Date | Actual_Date
S2P-001 | Requirements | Completed | 2026-07-01 | 2026-07-05
S2P-001 | Design | Completed | 2026-07-01 | 2026-07-05
S2P-001 | Development | Delayed | 2026-07-01 | 2026-07-05
S2P-001 | Testing | In Progress | 2026-07-01 | 2026-07-05
S2P-001 | Go Live | Pending | 2026-07-01 | 2026-07-05
S2P-002 | Requirements | Completed | 2026-07-01 | 2026-07-05
S2P-002 | Design | Completed | 2026-07-01 | 2026-07-05
S2P-002 | Development | Delayed | 2026-07-01 | 2026-07-05
S2P-002 | Testing | In Progress | 2026-07-01 | 2026-07-05
S2P-002 | Go Live | Pending | 2026-07-01 | 2026-07-05
S2P-003 | Requirements | Completed | 2026-07-01 | 2026-07-05
S2P-003 | Design | Completed | 2026-07-01 | 2026-07-05
S2P-003 | Development | Delayed | 2026-07-01 | 2026-07-05
S2P-003 | Testing | In Progress | 2026-07-01 | 2026-07-05
S2P-003 | Go Live | Pending | 2026-07-01 | 2026-07-05

## Risk_Register
Risk_ID | Project_ID | Risk | Severity | Status
R001 | S2P-001 | Risk 1 | Critical | Open
R002 | S2P-002 | Risk 2 | Medium | Open
R003 | S2P-002 | Risk 3 | High | Open
R004 | S2P-001 | Risk 4 | Medium | Open
R005 | S2P-002 | Risk 5 | Critical | Open
R006 | S2P-001 | Risk 6 | High | Open
R007 | S2P-002 | Risk 7 | Critical | Open
R008 | S2P-001 | Risk 8 | High | Open
R009 | S2P-003 | Risk 9 | High | Open

## Issue_Log
Issue_ID | Project_ID | Issue | Priority | Status
I001 | S2P-003 | Issue 1 | P1 | Resolved
I002 | S2P-003 | Issue 2 | P2 | Open
I003 | S2P-002 | Issue 3 | P3 | Resolved
I004 | S2P-001 | Issue 4 | P2 | Open
I005 | S2P-003 | Issue 5 | P3 | Open
I006 | S2P-001 | Issue 6 | P1 | Resolved
I007 | S2P-001 | Issue 7 | P2 | Open
I008 | S2P-002 | Issue 8 | P3 | Open
I009 | S2P-002 | Issue 9 | P1 | Open

## Resource_Allocation
Project_ID | Role | Utilization_%
S2P-001 | Developer | 90
S2P-001 | QA | 85
S2P-001 | PM | 75
S2P-002 | Developer | 90
S2P-002 | QA | 85
S2P-002 | PM | 75
S2P-003 | Developer | 90
S2P-003 | QA | 85
S2P-003 | PM | 75

## Stakeholder_Feedback
Project_ID | Week | Sentiment | Comment
S2P-001 | W1 | Neutral | Weekly review
S2P-001 | W1 | Neutral | Weekly review
S2P-002 | W1 | Negative | Weekly review
S2P-002 | W1 | Negative | Weekly review
S2P-003 | W1 | Positive | Weekly review
S2P-003 | W1 | Positive | Weekly review

## Weekly_Status
Project_ID | Week | Progress_% | Spend | Blockers | RAG
S2P-001 | W1 | 60 | 100000 | 1 | Amber
S2P-001 | W2 | 60 | 100000 | 1 | Amber
S2P-001 | W3 | 60 | 100000 | 1 | Amber
S2P-002 | W1 | 42 | 100000 | 1 | Amber
S2P-002 | W2 | 42 | 100000 | 1 | Amber
S2P-002 | W3 | 42 | 100000 | 1 | Amber
S2P-003 | W1 | 90 | 100000 | 1 | Amber
S2P-003 | W2 | 90 | 100000 | 1 | Amber
S2P-003 | W3 | 90 | 100000 | 1 | Amber