## Slide 1
Executive Summary
Automated monthly client-ready view generated from the analyzed project plans.
2
Projects
0
Green
0
Amber
2
Red
100% of analyzed views are currently red, which indicates that schedule recovery and execution control need executive attention before the next client reporting cycle.
This month at a glance
Risk is the most common lead driver.
Schedule pressure is the next-most common concern across the current plans.
UniSan S2P implementation remains red and should stay on the next escalation review list.
01

## Slide 2
Portfolio Health
RAG distribution, average score, and model validation point to a portfolio that is broadly under delivery pressure.
RAG Distribution
0
Green
0
Amber
2
Red
2 project plans were analyzed in this run, and every current view is red or amber-weighted enough to need active leadership attention.
53/100
Overall Score
50%
Validation Accuracy
The average score across all 2 analyzed project plans is 53/100. Validation against the embedded workbook health labels holds at 50%, which is directionally useful for leadership screening while keeping the reasoning transparent.
02

## Slide 3
Emerging Risks
Delay, budget burn, staffing pressure, and stakeholder confidence are emerging together rather than as isolated signals.
0
Budget Burn
1
Schedule Delays
2
Resource Issues
0
Stakeholder Concerns
Risk interpretation
1 projects are already more than two weeks behind, and 0 are spending ahead of delivery progress.
0 projects also carry two or more critical blockers, which means the schedule risk is likely to stay elevated unless escalation gets faster.
Resource utilization above 90% and neutral or negative stakeholder sentiment show that the pressure is visible both inside the delivery teams and with client-facing sponsors.
03

## Slide 4
Critical Projects
Top five red projects by score, ranked by the severity of the current delivery signal.
Project | Score | Reason
Zycus - UniSan S2P Implementation | 68.1 | About 61% of the plan duration has elapsed, while blended progress is 44% and 22% of due tasks are still incomplete
Zycus - Titan S2P Implementation | 38 | The plan carries 16 critical risks and 24 high risks
These projects should be reviewed first in the next escalation cadence because they combine the highest risk scores with clear delivery explanations.
04

## Slide 5
Recommendations
The next operating cycle should focus on recovery discipline, blocker escalation, and cleaner execution reporting.
01
Increase staffing where utilization is already above safe limits
Reassign or add capacity to the most constrained plans before schedule recovery work pushes the same teams further behind.
02
Escalate blocked projects through a daily unblock cadence
Use a standing review for critical blockers and P1 issues so execution stalls do not sit inside weekly status reports.
03
Rebaseline delayed milestones and enforce dated recovery plans
Reset dates at milestone level for the top red projects and review burn-versus-progress weekly until the gap narrows.
05

## Slide 6
Next Month Outlook
The near-term forecast improves only if the current red watchlist receives faster recovery actions than it did this month.
Forecast
Without intervention, the portfolio is likely to stay red-heavy next month because delay, cost, and blocker pressure are all elevated at the same time.
Expected improvements
1. Re-baselining the top five red projects should slow further schedule deterioration across the 1 projects already delayed by more than 14 days.
2. A tighter burn-versus-progress review should help contain the 0 projects currently spending ahead of delivery progress.
3. Daily blocker escalation and better status hygiene should improve confidence on the 0 heavily blocked projects and narrow the 0.4-point reporting gap in Zycus - UniSan S2P Implementation.
Project Plan B should stay on the watchlist next month because it remains Red and still carries a 0-point gap between weekly and task-level progress.
06